## Slide 1: Theory of change practical guide
For stress-testing an initial proposal
Lasted updated 11 November 2020

## Slide 2: Overview
Purpose
This is a practical guide for non-profit organisations in the initial stages of conceptualising and drafting a proposal for project/program funding. The guide aims to strengthen the proposal process by helping non-profits and funders develop and align early on clear outcomes that meet a demonstrated need and to ground assumptions on how the project will achieve the intended impact.
Instructions
There are two parts to this guide:
              Part I - Defining the problem, articulating the goal, identifying the outcomes and outlining the activities – was designed to be a self-guided exercise and takes about 2 hours to complete
              Part II – Theory of change mapping and listing of key assumptions and evidence – this should ideally be a group exercise facilitated by an experienced facilitator
Guiding questions are provided under each section and a worked example has also been created at the end of this deck for easy reference.
If you have any questions or need any clarifications, please feel free to reach out to Carol from the Just Cause team at carol@justcauseasia.org.

## Slide 3: Overview
Purpose
This is a practical guide for non-profit organisations in the initial stages of conceptualising and drafting a proposal for project/program funding. The guide aims to strengthen the proposal process by helping non-profits and funders develop and align early on clear outcomes that meet a demonstrated need and to ground assumptions on how the project will achieve the intended impact.
Instructions
There are two parts to this guide:
              Part I - Defining the problem, articulating the goal, identifying the outcomes and outlining the activities – was designed to be a self-guided exercise and takes about 2 hours to complete
              Part II – Theory of change mapping and listing of key assumptions and evidence – this should ideally be a group exercise facilitated by an experienced facilitator
Guiding questions are provided under each section and a worked example has also been created at the end of this deck for easy reference.
If you have any questions or need any clarifications, please feel free to reach out to Carol from the Just Cause team at carol@justcauseasia.org.

## Slide 4: Context
Problem
Who is your target group and what are their needs? How were the needs determined?
Goal
In no more than 2 lines, what is your overall programme/project goal?

## Slide 5: Target outcomes and activities
Outcomes
What are the main outcomes/changes you are trying to achieve? e.g low income women have more savings
Activities
How will you achieve the desired outcomes/changes? i.e. specific activities and outputs proposed to realise the outcomes outlined above? e.g. Introduce savings scheme to FDWs

## Slide 6: Theory of change mapping
e.g. Higher
financial status
End goal/ vision of success
Short-term
Med- to Long-term
ACTIVITIES: WHAT WE DO
OUTCOMES: THE DIFFERENCE WE MAKE
How do you think this programme/project will achieve the intended outcomes? Why do you think this will lead to the long term outcomes and end goal that your programme/project seeks to achieve?
e.g FDWs have more savings
e.g. Introduce savings scheme to FDWs
Insert your programme/ project’s end goal from slide 4
Insert the relevant outcomes from slide 5
Insert activities outlined in slide 5
Note: Boxes and arrows can be added/deleted accordingly

## Slide 7: Assumptions and evidence
No | Assumption | Evidence
1 |  | 
2 |  | 
3 |  | 
4 |  | 
5 |  | 
The main assumptions underlying our theory of change are:
What assumptions have you made? What evidence do you have (or will you seek) to validate these assumptions?

## Slide 8: Worked Example

## Slide 9: Context
Problem
Who is your target group and what are their needs? How were the needs determined?
Women from low income families often struggle to find meaningful employment due to the of experience, skills and opportunities in the workforce
Studies have shown that women are natural caregivers and provide a majority of informal care to spouses, parents, parents-in-law, friends and neighbours
The caregiving sector is seeing a shortage of workers and existing training curriculum does not include life skills training such as confidence building, which are essential to helping low income women gain and sustain employment
Goal
In no more than 2 lines, what is your overall programme/project goal?
To provide low income women opportunities to enter the caregiving workforce with certified skills and experience

## Slide 10: Target outcomes and activities
Outcomes
What are the main outcomes/changes you are trying to achieve? e.g low income women have more savings
More low income women employed as caregivers
Decreased shortage of workers in the caregiving sector
Activities
How will you achieve the desired outcomes/changes? i.e. specific activities and outputs proposed to realise the outcomes outlined above? e.g. Introduce savings scheme to FDWs
Work with industry partners to update certification curriculum to include life skills training
Recruit 80 low income women for training through introductory workshops and outreach campaigns
Deliver training courses and traineeships
Provide one-to-one support and mentoring to individual trainees
Help to place trainees in on-the-job traineeships, and eventually part-time and/or full-time employment
Outcomes should be expressed as a change (e.g. increased income, improved quality of life) and not just state of being (e.g. sustainable income, high quality education)

## Slide 11: Theory of change mapping
More job opportunities in the caregiving sector for low income women
More low income women are employable within the eldercare sector
More local low income women employed as caregivers
Short-term
Med- to Long-term
ACTIVITIES: WHAT WE DO
OUTCOMES: THE DIFFERENCE WE MAKE
How do you think this programme/project will achieve the intended outcomes? Why do you think this will lead to the long term outcomes and end goal that your programme/project seeks to achieve?
More low income women sign up for training in the caregiving sector
Trainees have increased confidence and skills in relation to the caregiving sector
More appropriate training is available for low-income women in the caregiving sector
Employers in the caregiving are more open to hiring low income women
Trainees receive greater emotional support
Deliver training courses (plus traineeships)
Develop updated curriculum
Provide one-to-one support and mentoring for individual trainees
Recruit trainees through introductory workshops and outreach campaigns
Job matching: e.g. facilitate interviews
Decreased shortage of workers in the caregiving sector

## Slide 12: Assumptions and evidence
No | Assumption | Evidence
1 | Updating the existing caregiver training curriculum will be sufficient to make training more appropriate for low income women | Based on feedback and suggestions provided through a focus group discussion with previous trainees
2 | There is a large enough pool of target women who are potentially interested in caregiving jobs and can be persuaded to sign up for the training through outreach campaigns | A market survey was conducted and more than 70% of the sample expressed interest in caregiving jobs
3 | With increased skills and confidence, trainees will be able to gain employment in the caregiving sector | Based on experience, the lack of skills and confidence are key reasons why low income women fail to complete the recruitment process
4 | Employment agencies are willing to hire low income women | Validated through phone interviews with 5 employment agencies
5 | That other external factors (such as childcare responsibilities) are not critical in preventing low income women from working | There are existing work schemes that has incorporated welfare and benefits (e.g childcare leave, time-off, part-time employment)
The main assumptions underlying our theory of change are:
What assumptions have you made? What evidence do you have (or will you seek) to validate these assumptions?
Evidence can be based on primary/secondary research and/or experience. If unavailable, indicate how you plan to validate it later as part of the project.

## Slide 13: Some tips and tricks!
Don’t be obsessed for getting it “right” or “perfect” the first time: this is meant to an iterative process for when your programme/project evolves
Be VERY honest with yourselves what impact/outcomes you are really trying to achieve: ideally, you want to focus on achievable changes
ToCs that are developed through a participatory process is more likely to result in more ownership and greater accountability: involve as many people as you can especially those who can help confirm/challenge your assumptions
Keep up to date with external evidence and what it means for your activities: understand that more often than not a social problem is complex and requires multiple parties and ways to tackle - you do not work alone
The process is more important than the end product so enjoy it: own the process, it’s more important to begin embedding a culture of change from within the organisation